﻿# NBU ActMenu - Phase 2 Roadmap (Owner / Effort / Risk / Reporting)

Last updated: 2026-03-04

Scope: Continue from Phase 1 baseline without breaking existing production flow.

## 1) Objectives

Improve student care visibility (attendance, risk, follow-up)

Reduce admin operations time

Increase reliability and governance readiness

Keep current LIFF check-in flow and data contracts stable

## 2) Workstreams and Ownership

| Workstream | Primary Owner | Supporting Owner(s) | Goal |

|---|---|---|---|

| Product & Requirements | Student Affairs Product Owner | Registrar, IT Office | Prioritize outcomes and acceptance criteria |

| Backend/API | Backend Engineer | DB Admin | Build reporting APIs, automation jobs |

| Frontend/Admin UI | Frontend Engineer | UX/QA | Dashboards, filters, exports, risk screens |

| Data/DB | Data Engineer / DB Admin | Backend Engineer | Query/index tuning, data quality |

| DevOps/Infra | DevOps Engineer | Backend Engineer | Deployment, monitoring, scaling |

| QA/UAT | QA Lead | Student Affairs Test Team | Test scenarios and regression control |

| Security & Compliance | Security/PDPA Owner | IT Office | Audit log, consent, retention baseline |

## 3) Timeline (30-60-90 Days)

## Phase 2A (Day 1-30): Stabilize + Visibility

### Features

1. Attendance Dashboard (base)

Metrics: check-ins by activity, day, month

Filters: faculty/program/year/date range

2. Export Reports

CSV export per activity (joined / not joined)

3. Reliability Baseline

Health endpoint

Structured error logging

Basic alerting

4. UX Fix Pack

Improve status/error messages and loading states

### Delivery table

| Item | Owner | Effort | Risk | Notes |

|---|---|---|---|---|

| Dashboard v1 | Frontend + Backend | M | Medium | Depends on query performance |

| CSV Export | Backend | S | Low | Reuse existing activity_checkins |

| Health/Logs | DevOps + Backend | S | Low | Fast win for ops |

| UX Fix Pack | Frontend | S | Low | No API contract change |

### Exit criteria

Admin can view attendance summary without SQL

CSV export available for at least 1 activity

Error triage time improved (logs usable)

## Phase 2B (Day 31-60): Proactive Student Care

### Features

1. Early Warning (v1)

Rule-based risk list (e.g., missed required activities)

2. Reminder / Follow-up Automation

Pre-activity reminders

Post-activity follow-up for absentees

3. Student Participation Timeline

Per-student activity history page

4. Role Separation (RBAC v1)

Read-only roles for advisor teams

### Delivery table

| Item | Owner | Effort | Risk | Notes |

|---|---|---|---|---|

| Early Warning v1 | Backend + Data | M | Medium | Rule definition alignment needed |

| Reminder jobs | Backend | M | Medium | Message quota and scheduling |

| Student timeline | Frontend + Backend | M | Medium | Data joins and pagination |

| RBAC v1 | Backend + Security | M | High | Access matrix must be approved |

### Exit criteria

Risk list visible and actionable weekly

Reminder/follow-up sent automatically for pilot activities

At least one advisor role can view read-only dashboards

## Phase 2C (Day 61-90): Governance + Scale

### Features

1. Audit Log

Track create/update/delete and sensitive access

2. PDPA/Consent Baseline

Consent recording and retention policy hooks

3. Performance & Scale Hardening

Query/index optimization from production data

Load test for peak event usage

4. Multi-OA Readiness (optional)

Configuration model to support more than one OA

### Delivery table

| Item | Owner | Effort | Risk | Notes |

|---|---|---|---|---|

| Audit log | Backend + Security | M | Medium | Storage growth considerations |

| PDPA baseline | Security + Backend | M | High | Policy/legal alignment |

| Scale hardening | DevOps + Backend + DB | M | Medium | Requires realistic load test |

| Multi-OA prep | Backend | M | Medium | Should be backward compatible |

### Exit criteria

Audit trail available for key admin actions

Retention/consent baseline documented and active

System validated under target peak load

## 4) Effort Legend

S = 1-3 dev days

M = 4-10 dev days

L = 11+ dev days

## 5) Risk Register (Top Items)

| Risk | Probability | Impact | Mitigation | Owner |

|---|---|---|---|---|

| Breaking existing LIFF flow | Medium | High | Keep API contracts stable, regression checklist mandatory | Backend Lead |

| LINE API behavior inconsistencies | Medium | Medium | Retry strategy, clear fallback UX, logging | Backend + Frontend |

| DB query slowdown with growth | Medium | High | Add indexes, analyze query plans, periodic tuning | DB Admin |

| Unauthorized admin data access | Low | High | RBAC rollout + audit logs + cookie hardening | Security |

| Deployment drift (stale build/config) | Medium | Medium | Standard runbook + PM2 reload checklist | DevOps |

## 6) Reporting Cadence

### Weekly report format

Progress (% by workstream)

Completed items this week

Blockers / decisions needed

Risk status (new/escalated/resolved)

Next week plan

### Suggested KPI dashboard

# students checked in / week

Attendance rate per key activity

# at-risk students detected (and contacted)

Time-to-generate report (before/after)

Production incidents / week

## 7) Definition of Done (Phase 2 items)

1. Feature behind tested path and no regression in Phase 1 core flow

2. API/docs updated

3. SQL migrations reviewed and reversible plan documented

4. Monitoring/logging in place for new critical paths

5. UAT sign-off from Student Affairs owner

## 8) Non-Breaking Technical Guardrails

1. Keep `/liff?activity=<key>` contract unchanged

2. Keep existing success/error response shape where already used by UI

3. Preserve `activity_checkins` dedup behavior (`UNIQUE (activity_key, line_user_id)`)

4. Preserve admin passkey gate until RBAC replacement is production-ready

5. No destructive schema changes without migration + rollback notes

## 9) Recommended Immediate Next Task (Sprint 1)

1. Build Attendance Dashboard v1

2. Add CSV export per activity

3. Add health endpoint + structured API error logs

4. Deliver weekly report template for stakeholders

---

Document owner: IT Office / Product Owner

Technical owner: Backend Lead

Review cycle: weekly (or per sprint)